## Todo
Priority | Category | Item
4 | Organization | Rework object hierarchy to require less work on changing textures or types
3 | Physics | Improve spring physics
3 | Physics | Improve jumping physics
3 | Gameplay | Implement direction-based interactions for spikes and etc.
3 | Gameplay | Implement enemy type with simple walk on floor AI (turn around when find dropoff)
3 | Physics | strict vs loose side interaction
3 | object type | water (physics slowdown; air timer)
3 | object type | up<->down crusher
3 | object type | up/down flame/fish jumper
3 | object type | horizontal left/right speed launcher
3 | object type | diagonal left/right spring
3 | object type | vertical up/down spring
3 | object type | variable orientation spikes
3 | object type | ice (friction decrease)
3 | object type | quicksand (sink; multsiple jump to escape)
3 | object type | rotating chainsaw
2 | Gameplay | Improve variety of procedurally generated levels
2 | GUI | Prompt to save edited level on any form of exit
2 | ViewManager | Implement fullscreen view
2 | Gameplay | Brainstorm and implement win feedback
2 | Gameplay | Brainstorm and implement death feedback
2 | Gameplay | Brainstorm and implement health system
2 | Physics | Implement a separate collisionbox that autocrops on load
2 | Physics | Implement choosing the shape of the collision polygon (circle/square)
2 | Slope Physics | Implement image mask -> polygon (1 - create polygon from coordinates of edge pixels; 2 - remove points from polygon and see how much area is reduced; 3 - if area is reduced < x%, allow point removal
2 | Performance | object tile chains/grids
2 | object type | fire flower
2 | object type | invincibility powerup
2 | object type | bumper
2 | object type | moving platform (left<->right or up<->down)
2 | object type | vine/ladder/metal mesh
2 | object type | collapseable bridge (reappear after offscreen)
2 | object type | pipe warp
1 | GUI | Include button to return to main menu at any time
1 | GUI | Add options menu screen
1 | ViewManager | Fix background tiling mechanism
1 | Editor | Implement background texture selection in editor
1 | Graphics | Brainstorm and implement a way to tag textures with different themes and entitytypes
0 | GUI | Implement support for double-clicking in game selection lists
0 | Physics | Reset player's momentum after respawn
0 | Organization | Remake non-object interactions as interactions
0 | LevelGen | A* player AI to assist in level generation

## Brainstorming
Cost | Value | Category | Item
|  | Procedural Generation | Data mine classic platformer levels for section patterns correlated to: - Previous sections - Difficulty level - Established level gimmicks Also take note of new types of sections Also take note of how to represent each type of section in a data structure (maybe use an array of objects mapped to points relating to the grid?) Also take note of how item placement may or may not be dependent on section type
|  | Game mechanic | you can be all the enemies and you try to stop the player from finishing the level; enemies have an AI component that operates a controllable mechanism which could also be used by a player; the gameplay could work either in splitscreen OR whenever an enemy becomes on-screen, it becomes operable by the enemy controller; best enemy on screen highlighted to show control

## Code snippets
// There is java.awt.geom.Area.intersect(Area) using the constructor Area(Shape) with your Polygon // and passing your Line2D as an Area to intersect will give you the Area which is intersected. // With great success, i used this approach: Area a = new Area(shape1); Area b = new Area(shape2); b.intersect(a); if (!b.isEmpty()) { //Shapes have non-empty intersection, so do you actions. //In case of need, actual intersection is in Area b. (it's a destructive operation) }

## Archive
1. Implement level serialization
1c. Game header data
1a. Object data
1b. Level header data
2b. Create new games for editing
2a. Load games for editing
2d. Select level within editor
2e. Save game within editor
2. Implement GUI for loading and saving games and levels
2c. Load games for playing
3a. Implement object type functionality
3c-i. Prevent moving list and camera simultaneously
3c-ii. Implement placeholder graphic for edit mode
3c. Improve edit camera
3d. Allow user to change grid size (between min and max)
3e. Fix playtesting side effects bug
3f. Fix slowdown with higher-density grids
Change behaviour of new Game button to show a modal input box asking for name
Remove game name textbox
Hide unnecessary buttons within level editor during play mode

## Procedural
[
[54 empty] | vine |  |  |  | ]
[58 empty] | [ | [12 empty] | - | - | - | - | - | - | - | -
[58 empty] | ] | [11 empty] | /
[58 empty] | [ | [10 empty] | /
[20 empty] | downhill | [37 empty] | ] | [9 empty] | /
[58 empty] | [ | [8 empty] | / | [5 empty] | split path
[57 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
[17 empty] | / | \ | [38 empty] | ¦
|  |  | straight | [6 empty] | - | - | - | - | - | - | / |  |  | \ | [17 empty] | No more than player jump span in width | [19 empty] | ¦ | [15 empty] | No more than player jump height
[9 empty] | / | [10 empty] | \ | [36 empty] | ¦ |  |  |  | wall
- | - | - | - | - | - | - | - | / | [11 empty] | ¦ | [12 empty] | - | - | - |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | /
[20 empty] | ¦ | [11 empty] | / |  |  |  | gap | [7 empty] | \
[9 empty] | uphill | [10 empty] | ¦ | [10 empty] | / | [13 empty] | \
[20 empty] | \ | - | - | - | - | - | - | - | - | - | / | [15 empty] | \ | [23 empty] | sections
[47 empty] | \ | - | - | - | - | - | - | - | [17 empty] | theme
subsections
[38 empty] | depends on difficulty level (random within range) | [35 empty] | type
[75 empty] | length | [5 empty] | items/hazards/enemies/etc
[16 empty] | Other types: | [58 empty] | height
liquid (water/elemental damage)